## Sheet1
L.O.S.S. Team • LAUNCH CHECKLIST
Overall Target Timeframe:
DEFINE: Strategy, Purpose, Goals | Target Timeframe:
Action Items | Responsible Person(s) | Due Date
Determine how we will establish credibility (Why would anyone in our county want our help?).
Determine what the LOSS team’s purpose is - state this in a concise mission statement
Determine how we will measure “success”
Create a high-level budget
Create Power Point overview of LOSS capturing the strategy, steps and team needs.
Determine what organization our LOSS team will be “housed” under (Fiscal Agent)
RECRUIT: Volunteers and Supporters | Target Timeframe:
Action Items | Responsible Person(s) | Due Date
Write a basic, short introduction to what LOSS is and how people can get involved.
Identify potential partners (see below) and meet with them (or email/call in a few cases - but most we will want face to face meetings). Three purposes: 1. Ask for volunteers, 2. Raise awareness, 3. Ask them for how they could see partnering with us go-forward. Not all of the below will be focused on all three of these. At the close of each meeting, be sure to ask, "Who else should I be connecting with?"
- Coroner/ME office (get buy-in, raise awareness). Many steps to prepare for this.
- SOS groups (ask for volunteers + raise awareness)
- Hotline (ask for volunteers + raise awareness)
- AFSP (ask for volunteers + raise awareness + ask how to partner)
- VA (ask for volunteers + raise awareness + ask how to partner)
- Hospices (raise awareness + ask how to partner)
- Mental Health Professionals. Make a list of Counseling Centers & choose at least XX number to visit in person with presentation. (ask for volunteers + raise awareness + ask how to partner)
- Other agencies including NAMI and MHA (ask for volunteers + raise awareness + ask how to partner)
- Hospitals/Hospital Chaplains (raise awareness + ask how to partner)
- Schools (raise awareness)
- Funeral Homes (raise awareness)
- Faith Communities - especially ones with a counseling dept and/or bereavement services. (raise awareness + ask for volunteers)
- Law Enforcement Chaplains (raise awareness + ask how to partner)
Determine how we help people evaluate whether they should/can volunteer with the LOSS team.
If not able/interested in on-scene work then we should recommend what capacity they can be involved in.
Create database of people invited to training.
Determine pre-requisites before becoming an active first responder volunteer. (PFA? QPR? On-Scene skills role plays? Background Check)
Create volunteer “job description” - one for LOSS team first responder and one for those acting as “leader” role on the scene.
RECRUIT: Volunteers and Supporters Continued: Create ADVISORY TEAM to help with launch & ongoing resources to leverage as needed - The team is most critical during start-up. It could also be an ongoing resource. Would be a low time-commitment and would meet on an adhoc basis after launch.
- Loss Survivors(s)
- Someone(s) from Coroner/Medical Examiner office
- Someone(s) from Law Enforcement
- Someone(s) from Mental Health Agency
- Military
- Local faith community leader(s)?
- Who else?
Newly Bereaved Resources and follow up support | Target Timeframe:
Action Items | Responsible Person(s) | Due Date
Determine On-Scene resources needed (less is more)
Develop resource list, cost, review list (evidence informed, safe messaging, etc)
Determine Follow Up/Post-Scene resources
Develop post-scene resource list, cost, then review list (evidence informed, safe messaging, etc).
Create time line for follow up with newly bereaved including cards on key dates.
DOCUMENT: Standard Operating Procedures (SOPs) | Target Timeframe:
Action Items | Responsible Person(s) | Due Date
Create pamphlet outlining what we do and how to reach us.
Create application each perspective volunteer will complete.
Create list of standard interview questions
Create database of all approved volunteers - determine what info needs to be included in db.
What materials would the team need to take with them when responding to a call. Blank pieces of paper, pen, phone #’s, crayons and coloring book, bottles of water, and make a list - a small “database” of important resources such as funeral homes, churches, cleaning companies, what else??
Determine driving logistics - need to arrive at scene in one car.
Get a phone and phone number.
Create SOP for scene activation and schedule.
Determine timing expectations. From time of call to time we arrive at scene.
Create Code of Conduct for volunteers.
Create templates and forms (incoming call form, post-scene report, what else?)
Get practical list of do’ s and don’ts from coroner and law enforcement.
How should coroner/police determine which scenes LOSS team are invited to? Our safety is critical.
Create job description of Loss Team Coordinator.
Determine data to track and create database
Develop on-call schedule.
Buy shirts/vests, or jackets, name badge, bags for volunteers.
Buy items to keep in bags (pen, paper, business card, trauma clean up resource to hand out, resource folders to hand out, tissues, mints, bottled water, etc)
TRAIN: Volunteers
Action Items
Determine what action we want people who completed info session and/or on- scene skills training to take for next steps.
Determine tool(s) we will use to train prospective volunteers to support bereaved on-scene and post-scene.
Each prospective volunteer that applies must be interviewed - make a list of questions we will ask & how we’ll divide up/coordinate this interview and decision- making process.
Create general info session for all prospective volunteers
Create on-scene skills training for first responders
Conduct interviewing & re-gather so decisions can be made.
Contact volunteers letting them know what role we would like them to consider
Write out agenda/flow of detailed tactical training including materials to be distributed.
Write up training materials.
Create folders with training materials.
MAINTAIN: Put Structure in Place to Support and Grow L.O.S.S. Team | Target Timeframe:
Action Items | Responsible Person(s) | Due Date
Determine funding related to sustaining and growing LOSS team.
How do we get and train new team members?
Identify opportunities for on-going volunteer training, self-care, and appreciation
Get volunteer team together regularly to discuss what’s working, what’s not, etc. *Establishing a sense of community among this group of people is very important*
MARKETING: | Target Timeframe:
Action Items | Responsible Person(s) | Due Date
Website
Social Media (Facebook, X, Instagram, etc.)
Press Release regarding launch
Promote Trainings
Do we have a specific name/logo/brand
Determine list of events LOSS team wants to be represented at (Out of Darkness Walk, Mental Health Day Fair, etc.). These could be manned by volunteers who want to help in some way but don’t want to be a first responder.
NOTES